## Closeout Schedule
Source: RCCD.pdf (509 pages) - 78 requirements. Every quote verified word-for-word against the cited page.
Spec Section | Section Title | Type | Item Required | Qty | Unit | Basis | Page | Spec Language (verbatim) | Checks | Notes | Unit Count | Total Qty | Count Source
00 73 13 | SUPPLEMENTARY GENERAL CONDITIONS TO THE CONTRACT | Extended Warranty | The Contractor will guarantee all materials and workmanship against original defects, except injury from prope | 2 | YR | after Acceptance by the Owner | 110 | The Contractor will guarantee all materials and workmanship against original defects, except injury from proper and usual wear when used for the purpose intended, for two years after Acceptance by the Owner, and will maintain all items in perfect condition during the period of guarantee. | PASS
00 73 13 | SUPPLEMENTARY GENERAL CONDITIONS TO THE CONTRACT | O&M Deliverable | prints - The Contractor shall provide two (2) prints of the as-built conditions, along with the rep | 2 | EA |  | 111 | The Contractor shall provide two (2) prints of the as-built conditions, along with the reproducible drawings themselves, to the Owner and one (1) set to the Architect. | PASS
00 73 13 | SUPPLEMENTARY GENERAL CONDITIONS TO THE CONTRACT | O&M Deliverable | set - The Contractor shall provide two (2) prints of the as-built conditions, along with the rep | 1 | SET |  | 111 | The Contractor shall provide two (2) prints of the as-built conditions, along with the reproducible drawings themselves, to the Owner and one (1) set to the Architect. | PASS
00 73 13 | SUPPLEMENTARY GENERAL CONDITIONS TO THE CONTRACT | O&M Deliverable | In addition, attach one complete set to each of the Operating and Maintenance Instructions/Manuals | 1 | SET |  | 111 | In addition, attach one complete set to each of the Operating and Maintenance Instructions/Manuals. | PASS
00 81 13 | GENERAL REQUIREMENTS | Extended Warranty | Performance and Payment Bonds shall be maintained in full force (warranty bond) for a period of two (2) years | 2 | YR |  | 132 | Performance and Payment Bonds shall be maintained in full force (warranty bond) for a period of two (2) years after the date of the Certificate for Final Payment. | PASS
00 81 13 | GENERAL REQUIREMENTS | Extended Warranty | For a period of two (2) years from the date of substantial completion, as evidenced by the date of final accep | 2 | YR | from the date of substantial completion | 142 | For a period of two (2) years from the date of substantial completion, as evidenced by the date of final acceptance of the work, the contractor warrants that work performed under this contract conforms to the contract requirements and is free of any defect of equipment, material or workmanship performed by the contractor or any of his subcontractors or suppliers. | PASS
01 70 00 | EXECUTION AND CLOSEOUT REQUIREMENTS | Quantity Not Specified | copy of site drawing signed by the Land Surveyor, that the elevations and locations of the work are in complia |  |  |  | 239 | Submit a copy of site drawing signed by the Land Surveyor, that the elevations and locations of the work are in compliance with Contract Documents. | PASS
01 70 00 | EXECUTION AND CLOSEOUT REQUIREMENTS | Quantity Not Specified | surveys and survey logs for the project record |  |  |  | 239 | Submit surveys and survey logs for the project record. | PASS
01 70 00 | EXECUTION AND CLOSEOUT REQUIREMENTS | Quantity Not Specified | written report that equipment or system has been properly installed and is functioning correctly |  |  |  | 244 | Submit a written report that equipment or system has been properly installed and is functioning correctly. | PASS
01 70 00 | EXECUTION AND CLOSEOUT REQUIREMENTS | Quantity Not Specified | For equipment or systems requiring seasonal operation, perform demonstration for other season within six month |  |  |  | 244 | For equipment or systems requiring seasonal operation, perform demonstration for other season within six months. | WARN | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
01 70 00 | EXECUTION AND CLOSEOUT REQUIREMENTS | Training | 8 hours minimum of demonstration and training | 8 | HR | minimum | 244 | Provide 8 hours minimum of demonstration and training. | PASS
01 70 00 | EXECUTION AND CLOSEOUT REQUIREMENTS | O&M Deliverable | bound hardcopies - operation and maintenance manuals for all installed equipment and devices, as-built drawin | 2 | EA |  | 245 | Provide operation and maintenance manuals for all installed equipment and devices, as-built drawings (PDF), and all inspection certificates as two (2) bound hardcopies and two (2) archival-grade (gold foil) DVDs. | PASS
01 70 00 | EXECUTION AND CLOSEOUT REQUIREMENTS | O&M Deliverable | archival-grade (gold foil) DVDs - operation and maintenance manuals for all installed equipment and devices, as-built drawin | 2 | EA |  | 245 | Provide operation and maintenance manuals for all installed equipment and devices, as-built drawings (PDF), and all inspection certificates as two (2) bound hardcopies and two (2) archival-grade (gold foil) DVDs. | PASS
01 70 00 | EXECUTION AND CLOSEOUT REQUIREMENTS | Quantity Not Specified | written certification that Contract Documents have been reviewed, work has been inspected, and that work is co |  |  |  | 245 | Submit written certification that Contract Documents have been reviewed, work has been inspected, and that work is complete in accordance with Contract Documents and ready for Architect's review. | PASS
01 70 00 | EXECUTION AND CLOSEOUT REQUIREMENTS | Maintenance Service | Maintenance Period | 1 | YR | from the Date of Substantial Completion | 245 | Maintenance Period: As indicated in specification sections or, if not indicated, not less than one year from the Date of Substantial Completion or the length of the specified warranty, whichever is longer. | WARN | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
01 78 00 | CLOSEOUT SUBMITTALS | O&M Deliverable | two sets of revised final documents in final form within 10 days after final inspection | 2 | SET |  | 253 | Submit two sets of revised final documents in final form within 10 days after final inspection. | PASS
01 78 00 | CLOSEOUT SUBMITTALS | O&M Deliverable | Two DVDs with All Project Record Submittals (Gold-Foil, Archival Grade DVDs) | 2 | EA |  | 253 | Two DVDs with All Project Record Submittals (Gold-Foil, Archival Grade DVDs) | PASS
01 78 00 | CLOSEOUT SUBMITTALS | O&M Deliverable | Maintain on site one set of the following record documents; record actual revisions to the Work: | 1 | SET |  | 254 | Maintain on site one set of the following record documents; record actual revisions to the Work: | PASS
01 78 00 | CLOSEOUT SUBMITTALS | O&M Deliverable | warranties and bonds, executed in duplicate by responsible Subcontractors, suppliers, and manufacturers, withi | 2 | EA |  | 255 | Obtain warranties and bonds, executed in duplicate by responsible Subcontractors, suppliers, and manufacturers, within 10 days after completion of the applicable item of work. | PASS
01 79 00 | DEMONSTRATION AND TRAINING | O&M Deliverable | Training Manuals | 1 | EA | for each attendee | 257 | Training Manuals: Provide training manual for each attendee; allow for minimum of two attendees per training session. | WARN | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules
01 79 00 | DEMONSTRATION AND TRAINING | O&M Deliverable | one extra copy of each training manual to be included with operation and maintenance data | 1 | EA | of each training manual to be included with operation and maintenance data | 257 | Provide one extra copy of each training manual to be included with operation and maintenance data. | WARN | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules
01 79 00 | DEMONSTRATION AND TRAINING | Quantity Not Specified | For equipment or systems requiring seasonal operation, perform demonstration for other season within six month |  |  |  | 258 | For equipment or systems requiring seasonal operation, perform demonstration for other season within six months. | WARN | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
01 79 00 | DEMONSTRATION AND TRAINING | Training | 8 hours of training | 8 | HR | minimum | 258 | Provide minimum 8 hours of training. | PASS
03 30 00 | CAST IN PLACE CONCRETE | Extended Warranty | Slabs with Moisture Vapor Reducing Admixture (MVRA) | 10 | YR |  | 272 | Slabs with Moisture Vapor Reducing Admixture (MVRA): Provide warranty to cover the cost of flooring failures due to moisture migration from slabs for ten years. | PASS
03 30 00 | CAST IN PLACE CONCRETE | Extended Warranty | Moisture Emission Reducing Curing and Sealing Compound | 10 | YR |  | 272 | Moisture Emission Reducing Curing and Sealing Compound: Provide warranty to cost of flooring delamination failures for 10 years. | PASS
09 51 00 | ACOUSTICAL CEILINGS | Attic Stock | 100 SF of Type A1 acoustical unit, for Owner's use in maintenance of project | 100 | SF |  | 292 | Provide 100 SF of Type A1 acoustical unit, for Owner's use in maintenance of project. | PASS
09 51 00 | ACOUSTICAL CEILINGS | Attic Stock | 1 box of Type A2 acoustical unit, for Owner's use in maintenance of project | 1 | BOX |  | 292 | Provide 1 box of Type A2 acoustical unit, for Owner's use in maintenance of project. | PASS
09 90 00 | PAINTS AND COATINGS | Attic Stock | 1 gallon of each color; store where directed | 1 | GAL | of each color | 296 | Supply 1 gallon of each color; store where directed. | WARN | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules
23 05 13 | MOTOR REQUIREMENTS FOR HVAC AND PLUMBING EQUIPMENT | Extended Warranty | five year manufacturer warranty for motors larger than 20 horsepower | 5 | YR |  | 301 | Provide five year manufacturer warranty for motors larger than 20 horsepower. | PASS
23 05 16 | EXPANSION FITTINGS AND LOOPS FOR HVAC PIPING | Spare Part | two sets of packing for each packed expansion joint | 2 | SET | for each packed expansion joint | 309 | Supply two sets of packing for each packed expansion joint. | WARN | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules
23 05 93 | TESTING, ADJUSTING, AND BALANCING FOR HVAC | Quantity Not Specified | final copies for Architect and for inclusion in operating and maintenance manuals |  |  |  | 326 | Provide final copies for Architect and for inclusion in operating and maintenance manuals. | PASS
23 09 13 | INSTRUMENTATION AND CONTROL DEVICES FOR HVAC | Maintenance Service | service and maintenance of control system for two years from Date of Substantial Completion | 2 | YR | from Date of Substantial Completion | 352 | Provide service and maintenance of control system for two years from Date of Substantial Completion. | WARN | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
23 09 23 | DIRECT DIGITAL CONTROL SYSTEM FOR HVAC | Extended Warranty | defective Work within a five year period after Substantial Completion | 5 | YR |  | 354 | Correct defective Work within a five year period after Substantial Completion. | PASS
23 09 23 | DIRECT DIGITAL CONTROL SYSTEM FOR HVAC | Extended Warranty | five year manufacturer's warranty for field programmable micro-processor based units | 5 | YR |  | 354 | Provide five year manufacturer's warranty for field programmable micro-processor based units. | PASS
23 09 23 | DIRECT DIGITAL CONTROL SYSTEM FOR HVAC | Maintenance Service | service and maintenance of energy management and control systems for one years from Date of Substantial Comple | 1 | YR | from Date of Substantial Completion | 354 | Provide service and maintenance of energy management and control systems for one years from Date of Substantial Completion. | WARN | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
23 09 23 | DIRECT DIGITAL CONTROL SYSTEM FOR HVAC | Maintenance Service | four complete inspections per year, two in each season, to inspect, calibrate, and adjust controls as required | 4 | EA | per year | 354 | Provide four complete inspections per year, two in each season, to inspect, calibrate, and adjust controls as required, and submit written reports. | WARN | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
23 09 23 | DIRECT DIGITAL CONTROL SYSTEM FOR HVAC | Maintenance Service | Make minimum of 4 complete normal inspections of approximately 4 hours duration in addition to normal service | 4 | EA | minimum | 355 | Make minimum of 4 complete normal inspections of approximately 4 hours duration in addition to normal service calls to inspect, calibrate, and adjust controls, and submit written reports. | PASS
23 09 23 | DIRECT DIGITAL CONTROL SYSTEM FOR HVAC | Training | service engineer to instruct Owner's representative in operation of systems plant and equipment for 2 day peri | 2 | DAY |  | 372 | Provide service engineer to instruct Owner's representative in operation of systems plant and equipment for 2 day period. | WARN | R9 labor hours not stated: 2 day(s) stated - hours per day not stated in spec
23 09 23 | DIRECT DIGITAL CONTROL SYSTEM FOR HVAC | Training | minimum of 8 hours dedicated instructor time | 8 | HR | minimum | 373 | Include a minimum of 8 hours dedicated instructor time. | PASS
23 21 13 | HYDRONIC PIPING | Special Tool | Operator | 1 | EA | for every ten plug valves minimum of one | 385 | Operator: One plug valve wrench for every ten plug valves minimum of one. | WARN | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules
23 21 23 | HYDRONIC PUMPS | Spare Part | Extra Pump Seals | 1 | SET | for each type and size of pump | 393 | Extra Pump Seals: One set for each type and size of pump. | WARN | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules
23 25 00 | HVAC WATER TREATMENT | Maintenance Service | service and maintenance of treatment systems for one year from Date of Substantial Completion | 1 | YR | from Date of Substantial Completion | 398 | Furnish service and maintenance of treatment systems for one year from Date of Substantial Completion. | WARN | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
23 25 00 | HVAC WATER TREATMENT | Quantity Not Specified | monthly technical service visits to perform field inspections and make water analysis on site |  |  | monthly - count not stated in this sentence, estimator must compute it | 398 | Provide monthly technical service visits to perform field inspections and make water analysis on site. | WARN | R10 CONFLICT: visits for this section are stated differently elsewhere (p.400) - raise an RFI ¦ R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
23 25 00 | HVAC WATER TREATMENT | Maintenance Service | two copies of field service report after each visit | 2 | EA |  | 398 | Submit two copies of field service report after each visit. | WARN | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
23 25 00 | HVAC WATER TREATMENT | Training | 2 hour training course for operating personnel, instructing them on installation, care, maintenance, testing, | 2 | HR |  | 398 | Include 2 hour training course for operating personnel, instructing them on installation, care, maintenance, testing, and operation of water treatment systems. | PASS
23 25 00 | HVAC WATER TREATMENT | Quantity Not Specified | sufficient chemicals for treatment and testing during warranty period |  |  |  | 398 | Supply sufficient chemicals for treatment and testing during warranty period. | PASS
23 25 00 | HVAC WATER TREATMENT | Quantity Not Specified | Training |  |  |  | 399 | Training: Train Owner's personnel on operation and maintenance of chemical treatment system. | WARN | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
23 25 00 | HVAC WATER TREATMENT | Training | two hours of instruction for two people | 2 | HR | minimum | 399 | Provide minimum of two hours of instruction for two people. | PASS
23 25 00 | HVAC WATER TREATMENT | Maintenance Service | service and maintenance of treatment systems for one year from Date of Substantial Completion | 1 | YR | from Date of Substantial Completion | 400 | Provide service and maintenance of treatment systems for one year from Date of Substantial Completion. | WARN | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
23 25 00 | HVAC WATER TREATMENT | Maintenance Service | bi-monthly (every 2 months) technical service visits for the first 6 months to perform field inspections and m | 2 | MO | bi-monthly - count not stated in this sentence, estimator must compute it | 400 | Provide bi-monthly (every 2 months) technical service visits for the first 6 months to perform field inspections and make water analysis on site. | WARN | R10 CONFLICT: visits for this section are stated differently elsewhere (p.398) - raise an RFI ¦ R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
23 64 23 | SCROLL WATER CHILLER | Spare Part | Extra Refrigerant | 1 | EA |  | 414 | Extra Refrigerant: One container. | PASS
23 64 23 | SCROLL WATER CHILLER | Spare Part | Extra Lubricating Oil | 1 | EA |  | 414 | Extra Lubricating Oil: One container. | PASS
23 64 23 | SCROLL WATER CHILLER | Extended Warranty | Manufacturer's Warranty | 5 | YR | minimum | 414 | Manufacturer's Warranty: Provide minimum Five year warranty to include coverage for materials and labor for compressor. | PASS
23 64 23 | SCROLL WATER CHILLER | Quantity Not Specified | Training |  |  |  | 418 | Training: Train Owner's personnel on operation and maintenance of system. | WARN | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
23 64 23 | SCROLL WATER CHILLER | Training | two hours of training | 2 | HR | minimum | 418 | Provide minimum of two hours of training. | PASS
23 64 23 | SCROLL WATER CHILLER | Maintenance Service | separate maintenance contract for the service and maintenance of chiller for 2 years from Date of Substantial | 2 | YR | from Date of Substantial Completion | 418 | Provide a separate maintenance contract for the service and maintenance of chiller for 2 years from Date of Substantial Completion. | WARN | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
23 64 26 | ROTARY-SCREW WATER CHILLERS | Spare Part | Extra Refrigerant | 1 | EA |  | 420 | Extra Refrigerant: One container. | PASS
23 64 26 | ROTARY-SCREW WATER CHILLERS | Spare Part | Extra Lubricating Oil | 1 | EA |  | 420 | Extra Lubricating Oil: One container. | PASS
23 64 26 | ROTARY-SCREW WATER CHILLERS | Extended Warranty | Manufacturer's Warranty | 2 | YR |  | 420 | Manufacturer's Warranty: 2 year parts and labor warranty for entire system. | PASS
23 64 26 | ROTARY-SCREW WATER CHILLERS | Extended Warranty | five year warranty to include coverage for materials only for compressor | 5 | YR | minimum | 420 | Provide minimum five year warranty to include coverage for materials only for compressor. | PASS
23 64 26 | ROTARY-SCREW WATER CHILLERS | Quantity Not Specified | Training |  |  |  | 424 | Training: Train Owner's personnel on operation and maintenance of system. | WARN | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
23 64 26 | ROTARY-SCREW WATER CHILLERS | Training | two hours of training | 2 | HR | minimum | 424 | Provide minimum of two hours of training. | PASS
23 64 26 | ROTARY-SCREW WATER CHILLERS | Maintenance Service | separate maintenance contract for the service and maintenance of chiller for 2 years from Date of Substantial | 2 | YR | from Date of Substantial Completion | 424 | Provide a separate maintenance contract for the service and maintenance of chiller for 2 years from Date of Substantial Completion. | WARN | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
23 73 13 | MODULAR CENTRAL-STATION AIR HANDLING UNITS | Spare Part | Extra Fan Belts | 1 | SET | for each unit | 426 | Extra Fan Belts: One set for each unit. | WARN | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules
23 73 13 | MODULAR CENTRAL-STATION AIR HANDLING UNITS | Spare Part | Extra Filters | 1 | SET | for each unit | 426 | Extra Filters: One set for each unit. | WARN | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules
23 73 13 | MODULAR CENTRAL-STATION AIR HANDLING UNITS | Extended Warranty | two year manufacturer parts and labor warranty covering repair or replacement due to defective materials or wo | 2 | YR | minimum | 426 | Provide minimum two year manufacturer parts and labor warranty covering repair or replacement due to defective materials or workmanship. | PASS
23 73 13 | MODULAR CENTRAL-STATION AIR HANDLING UNITS | Quantity Not Specified | Training |  |  |  | 432 | Training: Train Owner's personnel on operation and maintenance of system. | WARN | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
23 73 13 | MODULAR CENTRAL-STATION AIR HANDLING UNITS | Training | one day of training | 1 | DAY | minimum | 432 | Provide minimum of one day of training. | WARN | R9 labor hours not stated: 1 day(s) stated - hours per day not stated in spec
23 73 13 | MODULAR CENTRAL-STATION AIR HANDLING UNITS | Maintenance Service | service and maintenance of packaged roof top units for [2] years from Date of Substantial Completion | 2 | YR | from Date of Substantial Completion | 432 | Provide service and maintenance of packaged roof top units for [2] years from Date of Substantial Completion. | WARN | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
23 73 13 | MODULAR CENTRAL-STATION AIR HANDLING UNITS | Maintenance Service | routine maintenance service with a three month interval as maximum time period between calls | 3 | MO | three month interval - count not stated in this sentence, estimator must compute it | 432 | Provide routine maintenance service with a three month interval as maximum time period between calls. | WARN | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
23 73 13 | MODULAR CENTRAL-STATION AIR HANDLING UNITS | Maintenance Service | filter replacements - maintenance items as outlined in manufacturer's operating and maintenance data, including | 4 | EA | minimum | 433 | Include maintenance items as outlined in manufacturer's operating and maintenance data, including minimum of four (4) filter replacements, minimum of one fan belt replacement, and controls check-out, adjustments, and recalibration. | WARN | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
23 73 13 | MODULAR CENTRAL-STATION AIR HANDLING UNITS | Maintenance Service | fan belt replacement - maintenance items as outlined in manufacturer's operating and maintenance data, including | 1 | EA | minimum | 433 | Include maintenance items as outlined in manufacturer's operating and maintenance data, including minimum of four (4) filter replacements, minimum of one fan belt replacement, and controls check-out, adjustments, and recalibration. | WARN | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
23 81 01 | TERMINAL HEAT TRANSFER UNITS | Extended Warranty | five year manufacturers warranty for all motors | 5 | YR |  | 435 | Provide five year manufacturers warranty for all motors. | PASS
23 81 01 | TERMINAL HEAT TRANSFER UNITS | Extended Warranty | one year parts and labor warranty for enitre unit, from substitute and completion | 1 | YR |  | 435 | Provide one year parts and labor warranty for enitre unit, from substitute and completion. | PASS
23 81 01 | TERMINAL HEAT TRANSFER UNITS | Attic Stock | one (1) set of filters, with a final change immediately prior to occupancy | 1 | SET |  | 435 | Provide one (1) set of filters, with a final change immediately prior to occupancy. | PASS
26 27 26 | WIRING DEVICES | Attic Stock | two of each style, size, and finish wall plate | 2 | EA | of each style | 479 | Furnish two of each style, size, and finish wall plate. | WARN | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules
26 28 13 | FUSES | Special Tool | two fuse pullers | 2 | EA |  | 483 | Furnish two fuse pullers. | PASS
26 28 13 | FUSES | Spare Part | three of each size and type fuse installed | 3 | EA | of each size and type fuse installed | 483 | Furnish three of each size and type fuse installed. | WARN | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules

## Summary
Type | Rows
Maintenance Service | 15
Extended Warranty | 14
Quantity Not Specified | 13
O&M Deliverable | 11
Training | 9
Spare Part | 9
Attic Stock | 5
Special Tool | 2
Total | 78

## Labor
Row | Spec Section | Page | Item | Labor Type | Stated in spec | Hours | Status | How
10 | 01 70 00 | 244 | For equipment or systems requiring seasonal operation, perform demonstration for other season within six month | Owner training | - |  | Needs input | spec states the obligation but not the hours - estimator must price it
11 | 01 70 00 | 244 | 8 hours minimum of demonstration and training | Owner training | 8 h | 8 | Computed from spec | hours stated
15 | 01 70 00 | 245 | Maintenance Period | Post-completion service | - |  | Needs input | spec states the obligation but not the hours - estimator must price it
22 | 01 79 00 | 258 | For equipment or systems requiring seasonal operation, perform demonstration for other season within six month | Owner training | - |  | Needs input | spec states the obligation but not the hours - estimator must price it
23 | 01 79 00 | 258 | 8 hours of training | Owner training | 8 h | 8 | Computed from spec | hours stated
32 | 23 09 13 | 352 | service and maintenance of control system for two years from Date of Substantial Completion | Post-completion service | two year period |  | Needs input | spec states the obligation but not the hours - estimator must price it
35 | 23 09 23 | 354 | service and maintenance of energy management and control systems for one years from Date of Substantial Comple | Post-completion service | one year period |  | Needs input | spec states the obligation but not the hours - estimator must price it
36 | 23 09 23 | 354 | four complete inspections per year, two in each season, to inspect, calibrate, and adjust controls as required | Post-completion service | 4 inspections; per year |  | Needs input | spec states the obligation but not the hours - estimator must price it
37 | 23 09 23 | 355 | Make minimum of 4 complete normal inspections of approximately 4 hours duration in addition to normal service | Post-completion service | 4 h; 4 inspections | 16 | Computed from spec | 4 x 4 h stated
38 | 23 09 23 | 372 | service engineer to instruct Owner's representative in operation of systems plant and equipment for 2 day peri | Owner training | 2 day(s) |  | Needs input | 2 day(s) stated - hours per day not stated in spec
39 | 23 09 23 | 373 | minimum of 8 hours dedicated instructor time | Owner training | 8 h | 8 | Computed from spec | hours stated
42 | 23 25 00 | 398 | service and maintenance of treatment systems for one year from Date of Substantial Completion | Post-completion service | one year period |  | Needs input | spec states the obligation but not the hours - estimator must price it
43 | 23 25 00 | 398 | monthly technical service visits to perform field inspections and make water analysis on site | Post-completion service | monthly |  | Needs input | spec states the obligation but not the hours - estimator must price it
44 | 23 25 00 | 398 | two copies of field service report after each visit | Post-completion service | - |  | Needs input | spec states the obligation but not the hours - estimator must price it
45 | 23 25 00 | 398 | 2 hour training course for operating personnel, instructing them on installation, care, maintenance, testing, | Owner training | 2 h | 2 | Computed from spec | hours stated
47 | 23 25 00 | 399 | Training | Owner training | - |  | Needs input | spec states the obligation but not the hours - estimator must price it
48 | 23 25 00 | 399 | two hours of instruction for two people | Owner training | 2 h; 2 person(s) | 2 | Computed from spec | hours stated (instructor hours; 2 trainees = 4 trainee-hours)
49 | 23 25 00 | 400 | service and maintenance of treatment systems for one year from Date of Substantial Completion | Post-completion service | one year period |  | Needs input | spec states the obligation but not the hours - estimator must price it
50 | 23 25 00 | 400 | bi-monthly (every 2 months) technical service visits for the first 6 months to perform field inspections and m | Post-completion service | bi-monthly |  | Needs input | spec states the obligation but not the hours - estimator must price it
55 | 23 64 23 | 418 | Training | Owner training | - |  | Needs input | spec states the obligation but not the hours - estimator must price it
56 | 23 64 23 | 418 | two hours of training | Owner training | 2 h | 2 | Computed from spec | hours stated
57 | 23 64 23 | 418 | separate maintenance contract for the service and maintenance of chiller for 2 years from Date of Substantial | Post-completion service | 2 year period |  | Needs input | spec states the obligation but not the hours - estimator must price it
62 | 23 64 26 | 424 | Training | Owner training | - |  | Needs input | spec states the obligation but not the hours - estimator must price it
63 | 23 64 26 | 424 | two hours of training | Owner training | 2 h | 2 | Computed from spec | hours stated
64 | 23 64 26 | 424 | separate maintenance contract for the service and maintenance of chiller for 2 years from Date of Substantial | Post-completion service | 2 year period |  | Needs input | spec states the obligation but not the hours - estimator must price it
68 | 23 73 13 | 432 | Training | Owner training | - |  | Needs input | spec states the obligation but not the hours - estimator must price it
69 | 23 73 13 | 432 | one day of training | Owner training | 1 day(s) |  | Needs input | 1 day(s) stated - hours per day not stated in spec
70 | 23 73 13 | 432 | service and maintenance of packaged roof top units for [2] years from Date of Substantial Completion | Post-completion service | 2 year period |  | Needs input | spec states the obligation but not the hours - estimator must price it
71 | 23 73 13 | 432 | routine maintenance service with a three month interval as maximum time period between calls | Post-completion service | three month interval |  | Needs input | spec states the obligation but not the hours - estimator must price it
72 | 23 73 13 | 433 | filter replacements - maintenance items as outlined in manufacturer's operating and maintenance data, including | Post-completion service | - |  | Needs input | spec states the obligation but not the hours - estimator must price it
73 | 23 73 13 | 433 | fan belt replacement - maintenance items as outlined in manufacturer's operating and maintenance data, including | Post-completion service | - |  | Needs input | spec states the obligation but not the hours - estimator must price it

## Checks
Agent | Level | Row | Finding
1 Precision | WARN | 20 | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules
1 Precision | WARN | 21 | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules
1 Precision | WARN | 28 | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules
1 Precision | WARN | 30 | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules
1 Precision | WARN | 40 | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules
1 Precision | WARN | 41 | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules
1 Precision | WARN | 65 | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules
1 Precision | WARN | 66 | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules
1 Precision | WARN | 77 | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules
1 Precision | WARN | 79 | R8 quantity is per unit/size/type - total needs the count from drawings/equipment schedules
2 Quality | ERROR | 51 | R6 duplicate of row 44
2 Quality | ERROR | 51 | R6 quote repeated without a distinct item (padding)
2 Quality | WARN | 43 | R10 CONFLICT: visits for this section are stated differently elsewhere (p.400) - raise an RFI
2 Quality | WARN | 50 | R10 CONFLICT: visits for this section are stated differently elsewhere (p.398) - raise an RFI
2 Quality | WARN | - | R11 page 18: closeout keywords but no row - review manually
2 Quality | WARN | - | R11 page 130: closeout keywords but no row - review manually
2 Quality | WARN | - | R11 page 166: closeout keywords but no row - review manually
2 Quality | WARN | - | R11 page 235: closeout keywords but no row - review manually
2 Quality | WARN | - | R11 page 259: closeout keywords but no row - review manually
2 Quality | WARN | - | R11 page 348: closeout keywords but no row - review manually
2 Quality | WARN | - | R11 page 381: closeout keywords but no row - review manually
2 Quality | WARN | - | R11 page 397: closeout keywords but no row - review manually
2 Quality | WARN | - | R11 page 469: closeout keywords but no row - review manually
2 Quality | WARN | - | R11 page 488: closeout keywords but no row - review manually
2 Quality | INFO | - | 48 intentionally blank pages skipped
2 Quality | INFO | - | 79 candidate rows from 509 pages: Maintenance Service 16, Extended Warranty 14, Quantity Not Specified 13, O&M Deliverable 11, Training 9, Spare Part 9, Attic Stock 5, Special Tool 2
6 Drawings | INFO | - | 0 per-unit rows totalled from drawings/counts, 10 still need a count
3 Labor | WARN | 10 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 15 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 22 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 32 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 35 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 36 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 38 | R9 labor hours not stated: 2 day(s) stated - hours per day not stated in spec
3 Labor | WARN | 42 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 43 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 44 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 47 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 49 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 50 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 55 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 57 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 62 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 64 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 68 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 69 | R9 labor hours not stated: 1 day(s) stated - hours per day not stated in spec
3 Labor | WARN | 70 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 71 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 72 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | WARN | 73 | R9 labor hours not stated: spec states the obligation but not the hours - estimator must price it
3 Labor | INFO | - | 31 labor items; 8 computed from spec (48 h stated), 23 need estimator input
8 Div 23/26 | WARN | - | R16 26 28 18 ENCLOSED SWITCHES: calls for maintenance materials but lists none - RFI
8 Div 23/26 | INFO | - | R16 Division 23 HVAC: 21 sections, 12 with requirements, 0 flagged CHECK
8 Div 23/26 | INFO | - | R16 Division 26 Electrical: 12 sections, 2 with requirements, 1 flagged CHECK
4 Delivery | INFO | - | R12 file re-opened and matches verified data (78 rows)
7 Language | WARN | 33 | R15 quote has no common English words - check source
7 Language | INFO | - | R15 all sheets, headers and cells are English; quotes are original spec text
Run | INFO | - | Extraction and checks took 16 seconds

## Div 23-26 Coverage
Spec Section | Section Title | Pages | Closeout subsections found | Rows | Status
23 05 13 | MOTOR REQUIREMENTS FOR HVAC AND PLUMBING EQUIPMENT | 301-307 | 1.07 WARRANTY | 1 | OK - 1 requirement row(s)
23 05 16 | EXPANSION FITTINGS AND LOOPS FOR HVAC PIPING | 309-312 | 1.06 EXTRA MATERIALS | 1 | OK - 1 requirement row(s)
23 05 19 | METERS AND GAUGES FOR HVAC PIPING | 313-316 | 1.04 SUBMITTALS | 0 | No own closeout requirements (lists or cross-references only)
23 05 48 | VIBRATION AND SEISMIC CONTROLS FOR HVAC PIPING AND EQUIPMENT | 317-320 | - | 0 | No closeout requirements in this section
23 05 53 | IDENTIFICATION FOR HVAC PIPING AND EQUIPMENT | 321-324 | - | 0 | No closeout requirements in this section
23 05 93 | TESTING, ADJUSTING, AND BALANCING FOR HVAC | 325-334 | - | 1 | OK - 1 requirement row(s)
23 07 13 | DUCT INSULATION | 335-340 | - | 0 | No closeout requirements in this section
23 07 19 | HVAC PIPING INSULATION | 341-346 | - | 0 | No closeout requirements in this section
23 09 13 | INSTRUMENTATION AND CONTROL DEVICES FOR HVAC | 347-352 | 1.05 SUBMITTALS; 1.07 WARRANTY; 3.03 MAINTENANCE | 1 | OK - 1 requirement row(s)
23 09 23 | DIRECT DIGITAL CONTROL SYSTEM FOR HVAC | 353-374 | 1.05 SUBMITTALS; 1.08 WARRANTY; 1.09 MAINTENANCE SERVICE; 1.10 EXTRA MATERIALS; 3.03 MAINTENANCE; 3.03 MANUFACTURER'S FIELD SERVICES; 3.04 DEMONSTRATION AND INSTRUCTIONS | 7 | OK - 7 requirement row(s)
23 09 93 | SEQUENCE OF OPERATIONS FOR HAVAC CONTROLS | 375-378 | - | 0 | No closeout requirements in this section
23 21 13 | HYDRONIC PIPING | 379-388 | - | 1 | OK - 1 requirement row(s)
23 21 14 | HYDRONIC SPECIALTIES | 389-392 | - | 0 | No closeout requirements in this section
23 21 23 | HYDRONIC PUMPS | 393-394 | 1.05 SUBMITTALS | 1 | OK - 1 requirement row(s)
23 25 00 | HVAC WATER TREATMENT | 397-400 | 1.03 SUBMITTALS; 1.06 MAINTENANCE SERVICE; 1.07 MAINTENANCE MATERIALS; 3.05 CLOSEOUT ACTIVITIES; 3.06 MAINTENANCE | 9 | OK - 9 requirement row(s)
23 31 00 | HVAC DUCTS AND CASINGS | 401-405 | 3.06 MAINTENANCE | 0 | No own closeout requirements (lists or cross-references only)
23 33 00 | AIR DUCT ACCESSORIES | 407-411 | - | 0 | No closeout requirements in this section
23 64 23 | SCROLL WATER CHILLER | 413-418 | 2.05 SUBMITTALS; 2.08 WARRANTY; 4.02 MANUFACTURER'S FIELD SERVICES; 4.03 CLOSEOUT ACTIVITIES; 4.04 MAINTENANCE | 6 | OK - 6 requirement row(s)
23 64 26 | ROTARY-SCREW WATER CHILLERS | 419-424 | 2.05 SUBMITTALS; 2.08 WARRANTY; 4.02 MANUFACTURER'S FIELD SERVICES; 4.03 CLOSEOUT ACTIVITIES; 4.04 MAINTENANCE | 7 | OK - 7 requirement row(s)
23 73 13 | MODULAR CENTRAL-STATION AIR HANDLING UNITS | 425-433 | 1.04 SUBMITTALS; 1.08 WARRANTY; 3.04 CLOSEOUT ACTIVITIES; 3.05 MAINTENANCE; 4.04 MAINTENANCE | 9 | OK - 9 requirement row(s)
23 81 01 | TERMINAL HEAT TRANSFER UNITS | 435-439 | 1.03 SUBMITTALS; 1.05 WARRANTY; 1.06 EXTRA MATERIALS; 3.05 MAINTENANCE | 3 | OK - 3 requirement row(s)
26 05 01 | MINOR ELECTRICAL DEMOLITION | 441-442 | - | 0 | No closeout requirements in this section
26 05 19 | LOW-VOLTAGE ELECTRICAL POWER CONDUCTORS AND CABLES | 443-450 | - | 0 | No closeout requirements in this section
26 05 26 | GROUNDING AND BONDING FOR ELECTRICAL SYSTEMS | 451-453 | - | 0 | No closeout requirements in this section
26 05 29 | HANGERS AND SUPPORTS FOR ELECTRICAL SYSTEMS | 455-457 | - | 0 | No closeout requirements in this section
26 05 34 | CONDUIT | 459-462 | - | 0 | No closeout requirements in this section
26 05 37 | BOXES | 463-467 | - | 0 | No closeout requirements in this section
26 05 53 | IDENTIFICATION FOR ELECTRICAL SYSTEMS | 469-475 | - | 0 | No closeout requirements in this section
26 27 17 | EQUIPMENT WIRING | 477-478 | - | 0 | No closeout requirements in this section
26 27 26 | WIRING DEVICES | 479-482 | 1.06 EXTRA MATERIALS | 1 | OK - 1 requirement row(s)
26 28 13 | FUSES | 483-485 | 1.05 MAINTENANCE MATERIALS | 2 | OK - 2 requirement row(s)
26 28 18 | ENCLOSED SWITCHES | 487-491 | 1.05 SUBMITTALS | 0 | CHECK - section says 'furnish the following' maintenance materials but lists none (possible spec omission - consider an RFI)
26 29 13 | ENCLOSED CONTROLLERS | 493-499 | 3.06 CLOSEOUT ACTIVITIES | 0 | No own closeout requirements (lists or cross-references only)

## Rules
Strict rules applied to this schedule
R1 Every row comes from the PDF text. Nothing is generated, guessed or taken from general knowledge.
R2 'Spec Language (verbatim)' must appear word-for-word on the cited page (or run onto the next page). A sentence interrupted by the page header/footer is matched against the same page text with that page furniture removed - never against anything outside the cited pages.
R3 The cited Spec Section must exist in the document and must be the section printed on that page.
R4 Qty and Unit must be read from the quote itself. A number that is not in the quote is an error.
R5 Qty is empty only for 'Quantity Not Specified', and that type always has an empty Qty.
R6 No duplicate rows and no repeated quotes beyond the distinct items they contain (no padding).
R7 There is no target row count. The document decides how many rows there are.
R8 Quantities stated 'for each / per / of each' are NOT multiplied - the equipment count must come from the drawings or schedules and is flagged for the estimator.
R9 Labor hours are only calculated from hours, days, persons and visits stated in the quote. Missing factors are shown as 'Needs input', never assumed.
R10 Conflicting requirements for the same item are flagged on both rows, never silently resolved.
R11 Pages that mention closeout items but produced no row, and pages without readable text, are listed for manual review.
R12 The Excel file is re-opened and checked against the verified data. If any check fails, the file is not delivered.
R13 Scanned pages are read by OCR and every row from them is marked. Rows from pages with OCR confidence below 75% are removed and the page is listed for manual review.
R14 Per-unit quantities are totalled only from equipment tags/schedules found on the drawings or from an estimator's counts file, and the source of every count is written next to the total. 'Each type and size' is counted only from schedule columns (model/size/HP), never assumed.
R15 The delivered file is entirely in English. Spec quotes are the original English text and are never translated or reworded. Any non-English text blocks delivery.
R16 Every HVAC and Electrical section in the document (Divisions 23 and 26 in MasterFormat 2004, Divisions 15 and 16 in CSI 1995) is listed with its closeout subsections and row count. A section with closeout text but no extracted row is flagged CHECK; MasterFormat 2004 section numbers outside the Division 23/26 structure are flagged; a CSI 1995 five-digit number is listed but has no equivalent structure to be checked against.